{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["12月"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"12月","index":0,"n_rows":19,"n_cols":12,"rows_kept":19,"merged":[[0,0,0,11],[1,0,1,11],[2,0,2,11],[4,0,4,11],[13,0,13,11],[18,0,18,11]]}
["附件"]
["2025年12月份占用挖掘实施计划清单（12项）"]
["第一部分：建设项目占用挖掘实施计划清单（12项）"]
["序号","项目名称","申报单位","申报单位项目负责人","占用、挖掘目的","所在区域","道路名称","道路等级","占用、挖掘道路需求","新、改扩建、大修年份","是否属3、5年范围","初步审核意见"]
["市政类项目（道路、管线工程等）（8项）"]
[1,"前横路快速化改造工程","福州市勘测院有限公司","连礼茂13509356339","钻探施工","晋安区","福新东路","主干道","福新东路15个钻孔，其中沥青机动车道13孔、透水砖人行道2孔。每孔围挡占道3*9m，单孔挖掘0.3*0.3m","2013-12-01","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期30天"]
[2,"福州市上海西新村出让地块配套道路工程","福州市勘测院有限公司","周盛泽15359193106","钻探施工","台江区","斗池路","次干道","斗池路（西二环中路-白马中路段）共19个孔，均在人行道上，每孔围挡占道3*8m、单孔挖掘0.3*0.3m","2014-05-01","否","1、年度计划调整，拟同意挖掘申请\n2、许可施工期每孔1天、总工期21天"]
[3,"福州市污水管网完善提升二期工程-污水过河管道排查修复工程(鼓台2025年)","福州市城市排水有限公司","陈锹13600825976  徐鑫13559111930","钻探施工","台江区","白马南路","次干道","白马南路（奋斗里-浦东路）78号杆附近2个钻孔，每个钻孔挖掘沥青路面0.3*0.3平方米、围挡占道3*9平方米","2015-12-01","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期两个夜晚"]
["*4","仓山区牛道一路郭宅村一户一表改造项目","福州市自来水有限公司","高用道13859022063","自来水施工","仓山区","六合路","支路","六合路43号杆附近人行道透水砖30*1.5平方米","新改扩建     2023年11月","是","1、年度计划新增，拟同意挖掘申请\n2、许可施工期10天"]
["*△5","东岭路DN300给水管道改造工程","福州市自来水有限公司","黄英贵13950284730","自来水施工","仓山区","东岭路","主干道","东岭路（福湾路—万科翡翠之光）北侧（32-56号杆间）原管位占用挖掘人行道透水砖315*1.5平方米，经贸路口沥青路面15*1.5平方米","新改扩建    2022年9月","是","1、年度计划新增，拟同意挖掘申请\n2、许可施工期45天"]
["△6","乌山西路市政中压燃气工程","福州华润燃气有限公司","王倩玥15059182323","燃气施工","鼓楼区","乌山西路","主干道","乌山西路88号杆-104号杆间挖掘沥青非机动车道220*0.8平方米","2020年","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期开挖15天、试压接口5天"]
["*7","温福高铁（福建段）WFZQ-6标段","中国铁路南昌局集团有限公司福建铁路建设指挥部","王保锋18103698977","临时开口施工","仓山区","南江滨东大道","主干道","南江滨东大道137#杆附近南北两侧各开设施工临时通道，南侧拆除透水砖人行道12*3平方米开设一处跨度8米的施工临时出入口，同步拆除该处机非隔离带12*4平方米修复为车行道，移除137#路灯杆；北侧拆除透水砖人行道12*3平方米开设一处跨度8米的施工临时出入口，同步拆除该处机非隔离分带12*4平方米修复为车行道","新改扩建     2021年7月","是","1、年度计划新增，拟同意挖掘申请\n2、许可施工期开口10天、占用一年"]
["*△8","温福高铁（福建段）WFZQ-6标段","中国铁路南昌局集团有限公司福建铁路建设指挥部","丛晓卫18842484003","铁路建设","马尾区","福马路快安段","主干道","福马路快安段（辅道）38#杆-44#杆，铁路桥台施工挖掘辅道车行道20*3平方米，施工便道临时硬化主辅路间绿化带30*2平方米，施工围挡临时占用北侧辅道车行道、非机动车道150*8平方米，占用主道车行道30*2平方米","新改扩建      2021年6月","是","1、年度计划新增，拟同意挖掘占道申请\n2、许可施工期主车道占用5个月、辅道一年"]
["房建类项目（管线接驳、开口）（4项）"]
[9,"智谷创园（福兴园区）","福建省榕圣建设发展有限公司","傅磊磊13043528308","开口施工","晋安区","福兴大道","主干道","福兴大道西侧开设4米宽消防口，即拆除人行道金属栏杆4米","2013年1月","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期3天"]
[10,"左海滨江鸣翠项目","福州工业园区开发集团有限公司","赵佳毅18030013183","开口施工","仓山区","闽江大道","主干道","闽江大道339号杆附近挖掘水泥非机动车道7*6平方米、透水砖人行道3*4平方米，开设一个宽度4米的应急消防口，并迁移该处灯杆","2010年1月","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期7天"]
[11,"义序工业园区一期A地块工程","福州市园开新筑开发建设有限公司","陈森13655048119","开口及管线接驳施工","仓山区","南台大道","主干道","南台大道辅道55#杆处开设一处宽度4米次入口，同步拆除该处机非侧分带8*2平方米，迁移电力工井拆除透水砖人行道2*6平方米；电力接驳挖掘55#杆附近透水砖人行道5*1.5平方米、沥青非机动车道13*1.5平方米","2020-05-01","否","1、年度计划调整，拟同意挖掘申请\n2、许可施工期10天"]
[12,"宗地2022-56东部新城1#B出让地块（三江尚隽）电力接入工程","福州市土地房屋开发总公司","张营15880028681","电力接驳施工","仓山区","福峡路\n城峰路","主干道","①福峡路217#杆处挖掘人行道20*1.5平方米、沥青路面35*1.5平方米；②城峰路11号杆处挖掘水泥路面6*1.5平方米、人行道透水砖69*1.5平方米","2016年12月    2015年1月","否","1、年度计划新增，拟同意挖掘申请\n2、许可施工期6天"]
["备注：带Δ项目为涉及大型占道挖掘的项目（共3项） \n      带*项目为涉及新改扩建5年、大修3年路段的项目（共4项）"]